## Overview
TechTuber Roundtable
May 10, 2022 // Jeff's YouTube Studio, Shanghai
Event Date | 2022-05-10
Event Time | 10:00-14:40
Days Until Event: | -1268
Location | 1 Apple Park Way, Cupertino, California
Objectives | 1. Help viewers make informed smartphone purchase decisions
2. Drive downloads of the free "TechTuber Whitepaper"
3. Increase awareness of Jeff Su's YouTube channel
Format | Half-day offline event
Topics | - Android vs. iOS
- Which company makes the best smartphone?
- Who's the best...tech tuber? 😉
Team Meeting Notes | Link
Useful Links | Previous year | General
| Strategy Deck | Company brand guidelines
| Final working trix | Approvals deck
| Speaker list | Sandbox Brief

## Cost
Categories | Vendor | Cost (local currency) | Proposal | Comments
Promotion | Marques | 0
| Dave | 0
| The Verge | 10000 | Link
| Android Police | 8000 | Link
| SUB-TOTAL | 18000
Communications | Copywriting agency | 13200 | Link
Creatives | Creative agency | 8000 | Link
Deck Localization | Translation agency | 2000 | Link
Offline Setup | Marketing agency | 120000 | Link | We have a 10% discount with them
TOTAL |  | 161200

## RSVP Snapshot
RSVP Type Summary
TYPE | SEGMENT | REGISTERED | ATTENDED (unique visitors) | FILLED IN SURVEY
Eligible Registrations | Students (.edu emails) | 4 | 1 | 1
| Businesses (business emails) | 4 | 3 | 3
| VIPs (nominations) | 2 | 1 | 1
Others | Personal emails | 2 | - | -
| Competitors | 0 | - | -
| Marketing agencies | 0 | - | -
| Miscellaneous | 0 | - | -
| TOTAL RSVPs | 12
| TOTAL ELIGIBLE | 10 | 5 | 5
| 20% Drop-off | 8 | Attendance Rate | Survey Filled Rate
| 30% Drop-off TARGET | 7 | 50% | 100%
| 40% Drop-off | 6
Promotion Channel Summary
Channel | Promo channel type | Promo channel code | Total RSVP
Marques Brownlee | YouTube video | mb-yt-video
| Instagram | mb-ins
Dave2D | Email Newsletter | dave-email
| Website | dave-website
Paid Media | The Verge | pm-theverge
| Android Police | pm-androidp
Others | Nominations | Nominations
|  | TOTAL RSVP | 0

## Agenda
START TIME | MIN | TOPIC | SPEAKER | ROLE | HEADSHOT | SCRIPT | SLIDES | STATUS | COMMENTS
9:45 | 15 | (promotional videos) | - | - | - | - | Video folder
10:00 | 15 | Opening | Jeff Su | Host | Link | Link | Link
10:15 | 45 | The Future of Smartphones | Marques Brownlee | YouTuber | Link | Link | Link
11:00 | 15 | Interactive game | Jeff Su | Host | -
11:15 | 60 | Integration of Smartphones with the "Metaverse" | Dave Lee | YouTuber | Link | Link | Link
12:15 | 60 | Lunch | - | - | - | - | -
13:15 | 80 | Panel Discussion | Marques, Dave, Jeff | - | - | Link | Link
14:35 | 5 | Closing | Jeff Su | Host | - | Link | Link

## Promo Channels
|  |  | TODAY: | 2025-10-29
Channel Type | Channel Name | Channel Code | Asset Format/ Deliverables | Go Live Date | Link to asset | Owner | Status | Comments
Marques Brownlee | YouTube video | mb-yt-video | Video | 2022-03-10 | Link | Marques | Not Started
| Instagram | mb-ins | Instagram Post | 2022-03-12 | Link | Marques |  | Marques says he will do both a Instagram post and story
Dave Lee | Email Newsletter | dave-email | Text | 2022-03-10 | Link | Dave
| Website | dave-website | Text | 2022-03-11 | Link | Dave
Paid Media | The Verge | pm-theverge | Text | 2022-04-01 | Link | Dieter
| Android Police | pm-androidp | Text | 2022-04-01 | Link | Jane

## Comms Timeline
|  |  |  | EVENT DATE: | 2022-05-10
|  |  |  | TODAY: | 2025-10-29
Category | Type | Comms Message | CTA | Time | Send date | Status | Link to comms | Approved?
RSVP Confirmation | (automated) | Automatically generated message: We have received your sign up | - | - | - | N/A | Link | Y
Confirmation Email | Wave 1 | You have been approved to attend the offline event! | Event Webpage | 11:00 | 2022-04-25 |  | Link
| Wave 2 | You have been approved to attend the offline event! | Event Webpage | 11:00 | 2022-04-27 |  | Link
| Wave 3 | You have been approved to attend the offline event! | Event Webpage | 18:30 | 2022-04-29 |  | Link
Reminder Email | Wave 1 | Reminder: What to bring to the event | FAQ page | 18:30 | 2022-05-06 |  | Link
| Wave 2 | Reminder: What to bring to the event | FAQ page | 10:30 | 2022-05-09 |  | Link
Post-Event recap Email | (sent to all) | Event Recap | Watch recap video | 15:00 | 2022-05-20 |  | Link

## Action Items
|  |  | EVENT DATE: | 2022-05-10
|  |  | TODAY: | 2025-10-29
Category | Sub-category | Action Items | Owner | Deadline | Reference | Comment | STATUS
Prep Work | External Agency Selection | Select a minimum of 3 external agencies for RFP (request for proposal) | Jeff | 2021-10-25 | RFP |  | WIP
|  | Write agency brief | Jeff | 2021-10-26 | Doc |  | WIP
|  | Go through contracting process | Legal team | 2021-10-27 |  |  | Not Started
|  | Kick-off with agency | Jeff | 2021-10-28 | External deck |  | Not Started
| XFN Team Alignment | Brief Product team | Jeff | 2021-11-01 | Internal deck |  | WIP
|  | Brief Sales team | Jeff | 2021-11-02 | Internal deck |  | Not Started
|  | Kick-off meeting | Jeff | 2021-11-03 | Internal deck
|  | Schedule weekly project update meeting | Jeff | 2021-11-03 | Internal deck
...
Pre-Event | Content | Product team to provide speaker & topic | Product team POC
|  | Sales team to provide speaker & topic | Sales team POC
|  | Finalize all internal speakers | Jeff
|  | Submit speaker profile pictures, role, and 1 sentence description | Speakers
|  | Finalize agenda and narrative | Jeff
|  | Write up promotional materials based on speaker submissions | Copywriting team
...
| Promotion | Confirm promotion channels based on theme and narrative | Jeff
|  | Send brief to Marques, Dave, and Paid Media | PR team
|  | Review promotional content - Marques | Jeff
|  | Review promotional content - Dave | Jeff
|  | Review promotional content - Paid Media | Jeff
|  | Update and maintain "Promo Channels" tab | Jeff
| Creative | Produce event KV (key visual) | Creative agency |  | KV link
|  | Submit KV for approval | Jeff |  | Brand guidelines
|  | Design offline space | Creative agency
...
| Logistics (catch-all) | Schedule rehearsal with all speakers (and event agency) | Jeff
|  | Confirm game format | Jeff
|  | Confirm Q&A format | Speakers
|  | Speakers submit back up Q&A questions (optional) | Speakers
...
During Event | Logistics | Prepare 2 laptops (1 for presentation) | Jeff
|  | Real-time selection of winner during game session | Event agency
...
Post-Event | Logistics | Mail gift to winner | Event agency
|  | Import raw data into trix | Jeff
| Data | Post event analysis | Jeff
|  | Stakeholder debriefing | Jeff
|  | Input learnings into insights trix | Jeff
| Recap | Write recap | Copywriting team
|  | Proofread recap | Jeff
|  | Send recap EDM | Jeff

## Internal Whitelist
Instructions: Step 1: Use Command+F (or Ctrl+F) to check whether you're already included in this list. If Yes, you could leave this tab. If No, please proceed to Step 2. Step 2: Fill in Cloumn B through Column D RSVP Deadline: XXXX XXth, 11 pm
Team | Email | Please input your name (first name, last name) | De-Duped
Marketing | employee1@jsu.com |  | 1
Marketing | employee2@jsu.com |  | 1
Marketing | employee3@jsu.com |  | 1
Marketing | employee1@jsu.com |  | 2
Sales | sales1@jsu.com |  | 1
Sales | sales2@jsu.com |  | 1
Sales | sales3@jsu.com |  | 1
Team 1 | team1@jsu.com |  | 1
Team 2 | team2@jsu.com |  | 1
...

## Nominations
TEAM RESPONSIBLE | EMPLOYEE EMAIL | COMPANY | NAME | TITLE | EMAIL | MOBILE | DE-DUPED | STATUS | UID
Marketing | james@jsu.com | Microsoft | Bill Gates | CEO | bill@bgates.com | 404 989 9089 | 1 | Confirmed | MiMa89
Marketing | james@jsu.com | Ali Abdaal | Ali Abdaal | CEO | ali@aliabdaal.com | 102 192 9333 | 1 | Confirmed | AlMa33
Sales | ally@jsu.com | MKBHD | Maya Man | CMO | maya@mkbhd.com | 213 121 1223 | 1 | Rejected | MKSa23
Product | serena@jsu.com | Apple | Tim Cook | CEO | tim@cookie.com | 158 928 0293 | 1 | Rejected | ApPr93
...

## Seating Chart (lunch)
Table No. |  | First Name | Last Name | Company | Title
1-8ppl | 1 | Marques | Brownlee | MKBHD | CEO
| 2 | Elon | Musk | Tesla | CEO
| 3 | ....
4
5
6
7
8
2-9ppl | 1 | Dave | Lee | Dave2D | CEO
| 2 | Benjamin | Grubbs | Microsoft | VP of Marketing
| 3 | ...
4
5
6
7
8
9
3-9ppl | 1 | Jeff | Su | jeffsu.org | Peasant
| 2 | Lan | Diaresco | Apple | SVP
| 3 | ...
4
5
6
7
8
9

## Post-Event Analysis
Survey (Google Form link)
Raw output link
Snapshot
Key Performance Metrics | TechTuber Roundtable | Benchmark (similar events in the past) | % vs. Benchmark
Registration | 120 | 150 | -20%
Attended | 100 | 90 | 11.11%
Number of Surveys filled | ... | ... | -
Logistics Satisfaction Rate |  |  | -
Content Satisfaction Rate |  |  | -
Average watch time (min) |  |  | -
Average View Duration (%) |  |  | -
Satisfaction Breakdown
Segment | Attendance Rate (# attended / # registered) | Logistics Satisfaction Rate (# of 4 & 5 points / # of survey responses) | Content Satisfaction (# of 4 & 5 points / # of survey responses)
All Attendees | 83.33%
Students | 70%
Businesses | 86%
VIPs | ...
Q1: How did you find the overall logistics of this event? (with 5 being extremely satisfied and 1 being not at all)
Segment | 5 | 4 | 3 | 2 | 1
All Attendees
Students
Businesses
VIPs
Q2: How did you find the overall content of this event? (with 5 being extremely satisfied and 1 being not at all)
Segment | 5 | 4 | 3 | 2 | 1
All Attendees
Students
Businesses
VIPs
Q3: How useful did you find "The Future of Smartphones" session by Marques Brownlee?
Segment | 5 | 4 | 3 | 2 | 1
All Attendees | 85%
Students | 95%
Businesses | 75%
VIPs
Q4: How useful did you find "Integration of Smartphones with the "Metaverse"" session by Dave Lee?
Segment | 5 | 4 | 3 | 2 | 1
All Attendees
Students
Businesses
VIPs
Q5: What topics would you want to like to learn more about next time?
Segment | Internet of Things | Smart Cars | Smart Homes | Crypto | YouTube
All Attendees
Students
Businesses
VIPs
Q6: How did you hear about this event?
Segment | Marques' Social Media | Dave's Social Media | The Verge | Android Police | Other
All Attendees
Students
Businesses
VIPs
Q7: Anything else you'd like to tell us?
Segment
All Attendees
Students
Businesses
VIPs
Q8. Lowlights (room for improvement)

## Recap
Content Folder | Link
Recap | External | Internal
| Sizzle reel | Recap email
Event photos
Recap post
Reference | Previous year
Recap post (external)
Recap email (internal)
Recap videos

## RSVP Data
Google Forms: Link
Imported from Google Forms output spreadsheet (link)
👇🏻 IMPORTRANGE Function |  |  |  | Additional calculations
Timestamp | What's your name? | What's your email? | How did you hear about this event? | UID (unique ID) | Segment | Channel | De-Dupe
2021-10-04 15:32 | James Brown | jbrown@stanford.edu | MKBHD's Instagram Post | Stjb15 | Student | mb-ins | 1
2021-10-04 15:33 | Maggie Robbie | mrob@gmail.com | The Verge | Pemr36 | Personal | pm-theverge | 1
2021-10-04 15:33 | Philly Mange | pmange@microsoft.com | Dave2D's Email Newsletter | Bupm25 | Business | dave-email | 1
2021-10-04 15:34 | Snorlax Wong | snor@apple.com | Dave2D's Email Newsletter | Busn49 | Business | dave-email | 1
2021-10-04 15:34 | Billie Gaties | billie@microsoft.com | Android Police | Bubi07 | Business | pm-androidp | 1
2021-10-04 15:34 | Jennifer Lee | jlee@gmail.com | MKBHD's YouTube Video | Pejl24 | Personal | mb-yt-video | 1
2021-10-04 15:35 | Samantha Snessel | sam@tesla.com | MKBHD's YouTube Video | Busa45 | Business | mb-yt-video | 1
2021-10-04 15:36 | Cherry Lin | clin@emory.edu | MKBHD's YouTube Video | Stcl01 | Student | mb-yt-video | 1
2021-10-04 15:36 | Justin Tse | jtse@yale.edu | MKBHD's YouTube Video | Stjt14 | Student | mb-yt-video | 1
2021-10-04 15:37 | David Dai | ddai@umich.edu | Android Police | Stdd34 | Student | pm-androidp | 1
2023-02-11 19:27 | wen king yon | yonwk1973@gmail.com | MKBHD's YouTube Video
2023-03-05 02:47 | Nick, Elliott | nrelliott2019@gmail.com | MKBHD's Instagram Post
2023-03-11 20:26 | Monty | lollub.guo@gmail.com | Android Police
2023-04-05 02:59 | TEST | TEST@GMAIL.COM | MKBHD's YouTube Video
2023-04-05 03:00 | TEST 1 | TEST@csulb.edu | Android Police
2023-05-08 22:39 | George Faulkner | gfaulkner2021@elam.co.uk | MKBHD's YouTube Video
2023-07-10 22:54 | test | test@test.mail.com | MD
2023-07-10 22:57 | mememk | namek@memek.sch.id | meki
2023-08-25 18:05 | Sam T | samt@gmail.com | MKBHD's YouTube Video
2023-09-07 07:17 | tt | lausunning@gmail.com | MKBHD's YouTube Video
2023-12-01 16:57 | Catherine, Sherman | catherine@mcguckingroup.com | MKBHD's YouTube Video
2024-01-05 01:28 | Henry Hayes | henryllewellynhayes@gmail.com | MKBHD's YouTube Video
2024-01-17 12:15 | gbngbgb | gmhng@gg.vm | Android Police
2024-07-31 11:48 | This is, Atest | testing123@test.com | Android Police
2024-08-08 22:30 | Thian | hfthian@gmail.com | Trial
2024-12-09 01:43 | Hemanth kumar | hemanthkmr003@gmail.com | MKBHD's YouTube Video
2024-12-09 02:00 | Hemanth Kumar | hemanthkmr003@gmail.com | MKBHD's Instagram Post
2025-02-24 07:44 | fdsjfk sdfsf | sdfdsd@gmail.com | MKBHD's YouTube Video
2025-04-10 18:26 | adji | exajor@gmail.com | Dave2D's Email Newsletter
2025-07-29 20:31 | prateek | prateekkv150706@gmail.com | The Verge
2025-09-08 10:48 | Kulai | kulai@gmail.com | MKBHD's Instagram Post
2025-09-09 19:34 | Fatini Chelae | fatinichelae@gmail.com | MKBHD's YouTube Video

## Attendee Data
Updated after the event is completed
👇🏻 IMPORTRANGE Function |  |  | Additional calculations
UID | Name | Email | Segment | Channel
Stjb15 | James Brown | jbrown@stanford.edu | Student | mb-ins
Pemr36 | Maggie Robbie | mrob@gmail.com | Personal | pm-theverge
Bupm25 | Philly Mange | pmange@microsoft.com | Business | dave-email
Busn49 | Snorlax Wong | snor@apple.com | Business | dave-email
Bubi07 | Billie Gaties | billie@microsoft.com | Business | pm-androidp
AlMa33 | Ali Abdaal | ali@aliabdaal.com | VIP | nomination

## Survey Data
Imported from Google Forms output spreadsheet
👇🏻 IMPORTRANGE Function | [8 empty] | Additional calculations
UID | Your Name | Your Email | Q1 | Q2 | Q3 | Q4 | Q5 | ... | Segment | Channel
Stjb15 | James Brown | jbrown@stanford.edu | [6 empty] | Student | mb-ins
Pemr36 | Maggie Robbie | mrob@gmail.com | [6 empty] | Personal | pm-theverge
Bupm25 | Philly Mange | pmange@microsoft.com | [6 empty] | Business | dave-email
Busn49 | Snorlax Wong | snor@apple.com | [6 empty] | Business | dave-email
Bubi07 | Billie Gaties | billie@microsoft.com | [6 empty] | Business | pm-androidp
AlMa33 | Ali Abdaal | ali@aliabdaal.com | [6 empty] | VIP | nomination